## Overview
DEP Test Completion Report
Test Type | Sanity Testing | Project / BAU | Project
Project Name | DEP | Project Manager
Test Manager | Kenechuckwu Odachi | Test Expert | Olatunbosun Olamijulo
Test Design Start Date | 2023-09-04 | Test Design End Date | 2023-09-04
Test Execution Start Date | 2023-09-04 | Test Execution End Date | 2023-09-04
Sign Off
Name & Surname | Role | Date | Signature
Olatunbosun Olamijulo | Test Analyst | 2023-09-04
Kenechukwu Odachi | Peer Review

## Test Summary
Project Name | Retail Bid |  | Test Manager |  | Kenechukwu Odachi
Project Manager |  |  | Test Expert |  | Olatunbosun Olamijulo
2023-09-04 | Total Tests |  | Outstanding |  | Completed
| 6 |  | 0 (0%) |  | 6 (100%)
| Total Defects |  | Outstanding |  | Closed
| 0 |  | 0 (0%) |  | 0 (0%)
RAG Status | No passed / % Pass Rate) |  | 6 |  | 100%
Green | No of Defects / % of Critical & High) |  | 0 |  | 0%
Exit Criteria | Achieved | Comments
100% test coverage | Yes | None
0 Critical Defects Open | Yes | None | [5 empty] | Summary / Overview of Key Testing Issues
0 High Defect Open | Yes | None | [5 empty] | The validation of the PIN in performing transactions will be done in a controlled live environment, because this is not achievable on a test environment.
Business Walkthrough | N/A
Execution Statistics | Total Test Cases | Passed | Failed | Not Started | De-scoped & N/A | In Progress | On Hold
Number of tests | 6 | 6 | 0 | 0 | 0 | 0 | 0
Defect Statistics |  | Critical | High | Medium | Low | Total
Raised & Outstanding |  | 0 | 0 | 0 | 0 | 0
Closed |  | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 0 | 0 | 0

## Test Cases
Ref | Test Name | Test Scenario | Test Steps | Expected results | Comments | Status
DEP001 | Customer Information Input | Verify that the portal captures customer information correctly when entered by the desk officer/reviewer. | 1. Input valid customer information. 2. Save the customer information. 3. Retrieve the customer information from the portal. | The retrieved customer information should match the information entered in step 1. |  | Pass
DEP002 | Email Reminder Frequency | Verify that email reminders are sent to customers at the specified frequencies. | 1. Register a customer with a due date. 2. Verify that reminder emails are sent 2 months, 1 month, 1 week before the due date, and weekly after the due date. | Reminder emails are sent at the specified frequencies as described in the requirements. |  | Pass
DEP003 | Trigger Notification Mails | Verify that notification emails are triggered to customers' registered email addresses and relationship officers. | 1. Register a customer with a due date. 2. Trigger the notification process. 3. Check the email addresses where notification emails are sent. | Notification emails are sent to the customer's registered email address and the relationship officer's email address. |  | Pass
DEP004 | Notification Stop on Full Repatriation | Verify that notification is triggered for partial repatriation by the customer. | 1. Register a customer with a due date. 2. Initiate repatriation by the customer. 3. Verify that notification stops after full repatriation. | Notification stops when full repatriation is completed. |  | Pass
DEP005 | Notification on Partial Repatriation | Verify that notification is triggered for partial repatriation by the customer. | 1. Register a customer with a due date. 2. Initiate partial repatriation by the customer. 3. Verify that notification is triggered for partial repatriation. | Notification is triggered for partial repatriation. |  | Pass
DEP006 | Verify Report Generation | Verify that the Global Trade team can generate reports for all logged NXP requests. | 1. Access the report module. 2. Generate a report for all logged NXP requests. | A report containing all logged NXP requests is generated successfully. |  | Pass

## Defects
Defect ID | Testcase ID | Summary | Affected Test | Status | Priority | Comments | Screenshots
Note on C1: Olatunbosun Olamijulo: